## EXAMPLE 3-Year Ops Plan
3-YEAR OPERATIONAL PLAN TEMPLATE
START DATE |  |  | BUSINESS NAME |  | CREATOR |  |  | TITLE
2025-01-01 |  |  | Main Street Corp. |  | Bob B. |  |  | Sr. VP
EXECUTIVE SUMMARY
Project includes responsibilities for the Alpha Client Outreach project.
[10 empty] | YEAR ONE | [11 empty] | YEAR TWO | [11 empty] | YEAR THREE | [11 empty] | DO NOT ALTER CELL BELOW
PLAN DETAILS | [9 empty] | Y1Q1 |  |  | Y1Q2 |  |  | Y1Q3 |  |  | Y1Q4 |  |  | Y2Q1 |  |  | Y2Q2 |  |  | Y2Q3 |  |  | Y2Q4 |  |  | Y3Q1 |  |  | Y3Q2 |  |  | Y3Q3 |  |  | Y3Q4
GOAL | STRATEGY | PROJECT NAMES + TASK TITLES | RESPONSIBLE PARTY | RESOURCES NEEDED | START DATE | END DATE | # of Days | EVIDENCE OF SUCCESS | STATUS | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01
[10 empty] | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01
Kickoff Alpha |  | CATEGORY 1 | Kim P. |  | 2025-01-05 | 2026-04-21 | 337 |  | Complete | bar: 2025-01-01 to 2027-11-01
|  | P1 Task 1 | John K. | Marketing | 2025-01-05 | 2025-05-05 | 86 |  | Complete | bar: 2025-01-01 to 2025-05-01
|  | P1 Task 2 | Robert M. |  | 2025-04-02 | 2025-08-31 | 108 |  | In progress | bar: 2025-04-01 to 2025-08-01
|  | P1 Task 3 | Virginia W. |  | 2025-07-11 | 2025-10-15 | 69 |  | Incomplete | bar: 2025-07-01 to 2025-10-01
|  | P1 Task 4 |  |  | 2025-10-01 | 2025-12-31 | 66 | bar: 2025-10-01 to 2025-12-01
|  | P1 Task 5 |  |  | 2026-01-05 | 2026-03-11 | 48 | bar: 2026-01-01 to 2026-03-01
|  | P1 Task 6 |  |  | 2026-03-12 | 2026-04-21 | 29 | bar: 2026-03-01 to 2026-04-01
|  | CATEGORY 2 |  |  | 2025-04-22 | 2026-08-15 | 344 | bar: 2025-01-01 to 2027-11-01
|  | P2 Task 1 |  |  | 2025-04-22 | 2025-09-21 | 109 | bar: 2025-04-01 to 2025-09-01
|  | P2 Task 2 |  |  | 2025-05-30 | 2025-11-02 | 111 | bar: 2025-05-01 to 2025-11-01
|  | P2 Task 3 |  |  | 2025-08-05 | 2025-12-19 | 99 | bar: 2025-08-01 to 2025-12-01
|  | P2 Task 4 |  |  | 2025-10-25 | 2025-10-31 | 5 | bar: 2025-10-01
|  | P2 Task 5 |  |  | 2025-10-25 | 2026-03-26 | 109 | bar: 2025-10-01 to 2026-03-01
|  | P2 Task 6 |  |  | 2025-12-01 | 2026-08-15 | 185 | bar: 2025-12-01 to 2026-08-01
|  | CATEGORY 3 |  |  | 2026-02-14 | 2027-02-28 | 270 | bar: 2025-01-01 to 2027-11-01
|  | P3 Task 1 |  |  | 2026-02-14 | 2026-02-28 | 10 | bar: 2026-02-01
|  | P3 Task 2 |  |  | 2026-02-28 | 2026-06-28 | 85 | bar: 2026-02-01 to 2026-06-01
|  | P3 Task 3 |  |  | 2026-03-02 | 2026-06-28 | 85 | bar: 2026-03-01 to 2026-06-01
|  | P3 Task 4 |  |  | 2026-06-28 | 2026-07-11 | 10 | bar: 2026-06-01 to 2026-07-01
|  | P3 Task 5 |  |  | 2026-07-14 | 2026-09-27 | 54 | bar: 2026-07-01 to 2026-09-01
|  | P3 Task 6 |  |  | 2026-10-01 | 2027-02-28 | 107 | bar: 2026-10-01 to 2027-02-01
|  | CATEGORY 4 |  |  | 2026-12-01 | 2027-12-21 | 276 | bar: 2025-01-01 to 2027-11-01
|  | P4 Task 1 |  |  | 2026-12-01 | 2027-07-28 | 172 | bar: 2026-12-01 to 2027-07-01
|  | P4 Task 2 |  |  | 2027-03-01 | 2027-03-31 | 23 | bar: 2027-03-01
|  | P4 Task 3 |  |  | 2027-03-25 | 2027-11-01 | 158 | bar: 2027-03-01 to 2027-11-01
|  | P4 Task 4 |  |  | 2027-06-22 | 2027-12-21 | 131 | bar: 2027-06-01 to 2027-11-01
|  | P4 Task 5 |  |  | 2027-09-30 | 2027-10-10 | 7 | bar: 2027-09-01 to 2027-10-01
|  | P4 Task 6 |  |  | 2027-12-01 | 2027-12-15 | 11
CLICK HERE TO CREATE IN SMARTSHEET | bar: 2025-01-01 to 2026-12-01
Formulas:
CREATOR = MIN([CREATOR, row below]:G18)
CREATOR = MIN(IF([CREATOR, row below]:G32="","",[CREATOR, row below]:G32))

## BLANK 3-Year Ops Plan
3-YEAR OPERATIONAL PLAN TEMPLATE
Enter initial Start Date below to populate Timeline dates.
START DATE |  |  | BUSINESS NAME |  | CREATOR |  |  | TITLE
2025-01-01 |  |  | Main Street Corp. |  | Bob B. |  |  | Sr. VP
EXECUTIVE SUMMARY
Project includes responsibilities for the Alpha Client Outreach project.
Enter each Task Start and End Date per Project, below. Project Dates and # of Days will calculate automatically. | [9 empty] | YEAR ONE | [11 empty] | YEAR TWO | [11 empty] | YEAR THREE | [11 empty] | DO NOT ALTER CELL BELOW
PLAN DETAILS | [9 empty] | Y1Q1 |  |  | Y1Q2 |  |  | Y1Q3 |  |  | Y1Q4 |  |  | Y2Q1 |  |  | Y2Q2 |  |  | Y2Q3 |  |  | Y2Q4 |  |  | Y3Q1 |  |  | Y3Q2 |  |  | Y3Q3 |  |  | Y3Q4
GOAL | STRATEGY | PROJECT NAMES + TASK TITLES | RESPONSIBLE PARTY | RESOURCES NEEDED | START DATE | END DATE | # of Days | EVIDENCE OF SUCCESS | STATUS | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01
[10 empty] | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01
|  | CATEGORY 1 |  |  |  |  | 0
|  | P1 Task 1 |  |  |  |  | 0
|  | P1 Task 2 |  |  |  |  | 0
|  | P1 Task 3 |  |  |  |  | 0
|  | P1 Task 4 |  |  |  |  | 0
|  | P1 Task 5 |  |  |  |  | 0
|  | P1 Task 6 |  |  |  |  | 0
|  | CATEGORY 2 |  |  |  |  | 0
|  | P2 Task 1 |  |  |  |  | 0
|  | P2 Task 2 |  |  |  |  | 0
|  | P2 Task 3 |  |  |  |  | 0
|  | P2 Task 4 |  |  |  |  | 0
|  | P2 Task 5 |  |  |  |  | 0
|  | P2 Task 6 |  |  |  |  | 0
|  | CATEGORY 3 |  |  |  |  | 0
|  | P3 Task 1 |  |  |  |  | 0
|  | P3 Task 2 |  |  |  |  | 0
|  | P3 Task 3 |  |  |  |  | 0
|  | P3 Task 4 |  |  |  |  | 0
|  | P3 Task 5 |  |  |  |  | 0
|  | P3 Task 6 |  |  |  |  | 0
|  | CATEGORY 4 |  |  |  |  | 0
|  | P4 Task 1 |  |  |  |  | 0
|  | P4 Task 2 |  |  |  |  | 0
|  | P4 Task 3 |  |  |  |  | 0
|  | P4 Task 4 |  |  |  |  | 0
|  | P4 Task 5 |  |  |  |  | 0
|  | P4 Task 6 |  |  |  |  | 0

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.